## Checklist
Texas Water Development Board
CLOSING CHECKLIST - BONDS
Pre-Adoption of Bond Ordinance | Completed
Commitment for funding is approved at TWDB Board Meeting | TWDB
TWDB sends Board Action Letter to Borrower shortly after commitment for funding is approved | TWDB
Borrower responds to Board Action Letter by contacting TWDB with anticipated dates for adoption of its bond ordinance resolution and closing date
TWDB Financial Analyst works with Borrower to confirm anticipated closing date and closing timeline | TWDB
Borrower creates draft bond ordinance resolution and Private Placement Memorandum and provides drafts to TWDB Attorney and TWDB Financial Analyst within 20 days prior to the adoption date
TWDB Financial Analyst provides interest rates to Borrower 5 business days prior to the adoption date | TWDB
Borrower holds council meeting to approve bond ordinance resolution
Post-Adoption of Bond Ordinance | Completed
Borrower’s consultants work on finalizing closing docs (TWDB-0603)
TWDB Outlays Team creates Outlays workbook and sends to Borrower | TWDB
TWDB Engineer contacts Borrower/Consultants to create budget | TWDB
If budget changes or needs to be revised – Borrower/Consultants send changes to TWDB Engineer to update the Outlay workbook
Borrower's Financial Analyst sends invoice or signed verification page with completed Outlays workbook back to TWDB Outlays Team for processing
Borrower's Financial Analyst provides draft closing memorandum that reflects the Outlay invoices to TWDB Financial Analyst
Submittal of Final Documents & Final Closing Steps | Completed
Eight business days prior to the closing date, Borrower provides all final closing documents to the TWDB Financial Analyst and TWDB Attorney:
1. Executed Escrow Agreement (if applicable) [created by Bond Counsel]
2. TWDB Vendor Set-Up or Direct Deposit Form [attached to Board Action Letter, completed by Borrower, please send back asap]
3. Sufficiency of Funds Statement [created by external Engineer or consultant]
4. Wire Transfer Letter (for wire transfers only) [attached to Board Action Letter, filled out by Borrower]
5. Agreement Execution Resolution [filled out by Bond Counsel, labeled as TWDB-0169 at http://www.twdb.texas.gov/financial/instructions/index.asp]
6. Executed Consultant Contract(s), may include: [filled out by consultant]
a. Scope of Work, including detailed project area map identifying tasks to be performed
b. Budget with task budget breakdown
c. Schedule, including any required public meetings
d. List of deliverables
e. Fee Schedule, if applicable
7. Final award documents from FEMA/TDEM (FIF Category 3 only) [created by Borrower]
8. Documentation of in-kind contributions or local funds (cash contributions) [completed by Borrower]
9. Bond Ordinance or Resolution adopting the issuance [created by Bond Counsel]
10. Debt Service Schedule, semi-annual [created by Borrower’s Financial Analyst]
11. Financial Advisor’s Closing Instructions [created by Borrower’s Financial Analyst]
12. Executed Paying Agent Agreement [created by Bond Counsel]
13. Private Placement Memorandum – with all attachments [created by Borrower’s Financial Analyst]
14. Blanket Issuer Letter of Representations (BLOR) [sent by TWDB Financial Analyst, filled out by Borrower]
15. Bond Counsel Opinion [created by Bond Counsel]
16. No Litigation Certificate [created by Bond Counsel]
17. No Arbitrage/Federal Tax Certificate [created by Bond Counsel]
18. Five business days prior to the closing date, Borrower provides AG Opinion [created by Bond Counsel]
19. Five business days prior to the closing date, Borrower provides Comptroller's Certificate [created by Bond Counsel]
TWDB reviews closing documents and provides comments/corrections to Borrower as needed | TWDB
Closing and distribution of funds | TWDB